## Test report
Test report
Project Name | Calculator System
Stage | Sprint 1
Project Code
Test Environment Setup Description | Winform
Tester | Tran Quy
Tran An Thuyen
Test Result | PASS
FAIL
SKIPPED
NOT IMPLEMENTED
No | Testcase ID | Function Name | Sheet Name | Create Date
1 | A - X | Addition | Addition Function | 2024-02-15
2 | S - X | Subtraction | Subtraction Function | 2024-02-15
3 | M - X | Multiplication | Multiplication Function | 2024-02-15
4 | D - X | Division | Division Function | 2024-02-15
5 | M - X | Modulus | Modulus Function | 2024-02-15
6 | C - X | Clear | Clear Function | 2024-02-15
Note: X is Number

## Addition Function
Module |  | Addition
Code |  | AC
Check requirement
Tester |  | Tran Quy
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 4 | 4 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 4 | 4 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | AC - 1 | Addition | Check ComboBox |  | 1. Click on ComboBox 2. Choose "Addition" in ComboBox. |  | Show wrong title in UI, title name must "ADDITION" | 2024-02-16 | PASS |  | PASS | Tran Quy
2 | AC - 2 | Addition | Enter value |  | 1. Click on text file of First number and Second number. 2. Enter the value. | First number ="45" Second number = "25" | can't input number on text box | 2024-02-16 | PASS |  | PASS | Tran Quy
3 | AC - 3 | Addition | Check number |  | 1. Click on text file of First number and Second number. 2. Enter the value. 3. Click on Calculate. | First number ="45" Second number = "25" | Show wrong: " input in text field must a number ". | 2024-02-16 | PASS |  | PASS | Tran Quy
4 | AC - 4 | Addition | Calculate |  | 1. Click on Calculate. | First number ="45" Second number = "25" result = 70 | Wrong result | 2024-02-16 | PASS |  | PASS | Tran Quy

## Subtraction Function
Module |  | Subtraction
Code |  | SC
Check requirement
Tester |  | Tran Quy
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 4 | 4 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 4 | 4 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | SC - 1 | Subtraction | Check ComboBox |  | 1. Click on ComboBox 2. Choose "Subtraction" in ComboBox. |  | Show wrong title in UI, title name must "SUBTRACTION" | 2024-02-17 | PASS |  | PASS | Tran Quy
2 | SC - 2 | Subtraction | Enter value |  | 1. Click on text file of First number and Second number. 2. Enter the value. | First number ="35.3" Second number = "25.1" | can't input number on text box | 2024-02-17 | PASS |  | PASS | Tran Quy
3 | SC - 3 | Subtraction | Check number |  | 1. Click on text file of First number and Second number. 2. Enter the value. 3. Click on Calculate. | First number ="35.3" Second number = "25.1" | Show wrong: " input in text field must a number ". | 2024-02-17 | PASS |  | PASS | Tran Quy
4 | SC - 4 | Subtraction | Calculate |  | 1. Click on Calculate. | First number ="35.3" Second number = "25.1" result = 10.2 | Wrong result | 2024-02-17 | PASS |  | PASS | Tran Quy

## Multiplication Function
Module |  | Multiplication
Code |  | MC
Check requirement
Tester |  | Tran An Thuyen
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 4 | 4 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 4 | 4 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | MC - 1 | Multiplication | Check ComboBox |  | 1. Click on ComboBox 2. Choose "Multiplication" in ComboBox. |  | Show wrong title in UI, title name must "MULTIPLICATIOIN" | 2024-02-17 | PASS |  | PASS | Tran An Thuyen
2 | MC - 2 | Multiplication | Enter value |  | 1. Click on text file of First number and Second number. 2. Enter the value. | First number ="-0.25" Second number = "25" | can't input number on text box | 2024-02-17 | PASS |  | PASS | Tran An Thuyen
3 | MC - 3 | Multiplication | Check number |  | 1. Click on text file of First number and Second number. 2. Enter the value. 3. Click on Calculate. | First number ="-0.25" Second number = "25" | Show wrong: " input in text field must a number ". | 2024-02-17 | PASS |  | PASS | Tran An Thuyen
4 | MC - 4 | Multiplication | Calculate |  | 1. Click on Calculate. | First number ="-0.25" Second number = "25" result = -6.25 | Wrong result | 2024-02-17 | PASS |  | PASS | Tran An Thuyen

## Division Function
Module |  | Division
Code |  | CD
Check requirement
Tester |  | Tran An Thuyen
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 5 | 5 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 5 | 5 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | CD - 1 | Division | Check ComboBox |  | 1. Click on ComboBox 2. Choose "Division" in ComboBox. |  | Show wrong title in UI, title name must "DIVISION" | 2024-02-18 | PASS |  | PASS | Tran An Thuyen
2 | CD - 2 | Division | Enter value |  | 1. Click on text file of First number and Second number. 2. Enter the value. | First number ="2.5" Second number = "5" | Can't input number on text box | 2024-02-18 | PASS |  | PASS | Tran An Thuyen
3 | CD - 3 | Division | Check number |  | 1. Click on text file of First number and Second number. 2. Enter the value. 3. Click on Calculate. | First number ="2.5" Second number = "5" | Show wrong: " input in text field must a number ". | 2024-02-18 | PASS |  | PASS | Tran An Thuyen
4 | CD - 4 | Division | Calculate |  | 1. Click on text file of First number and Second number. 2. Enter the value. 3. Click on Calculate. | First number ="2.5" Second number = "0" give message: can't divided by 0. | Cannot be divided by 0 | 2024-02-18 | PASS |  | PASS | Tran An Thuyen
5 | CD - 5 | Division | Calculate |  | 1. Click on Calculate. | First number ="2.5" Second number = "5" result = 0.5 | Wrong result | 2024-02-18 | PASS |  | PASS | Tran An Thuyen

## Modulus Function
Module |  | Modulus
Code |  | MC
Check requirement
Tester |  | Tran An Thuyen
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 5 | 5 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 5 | 5 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | MC - 1 | Modulus | Check ComboBox |  | 1. Click on ComboBox 2. Choose "Modulus" in ComboBox. |  | Show wrong title in UI, title name must "MODULUS" | 2024-02-18 | PASS |  | PASS | Tran An Thuyen
2 | MC - 2 | Modulus | Enter value |  | 1. Click on text file of First number and Second number. 2. Enter the value. | First number ="21" Second number = "5" | Can't input number on text box | 2024-02-18 | PASS |  | PASS | Tran An Thuyen
3 | MC - 3 | Modulus | Check number |  | 1. Click on text file of First number and Second number. 2. Enter the value. 3. Click on Calculate. | First number ="21" Second number = "5" | Show wrong: " input in text field must a number ". | 2024-02-18 | PASS |  | PASS | Tran An Thuyen
4 | MC - 4 | Modulus | Calculate |  | 1. Click on text file of First number and Second number. 2. Enter the value. 3. Click on Calculate. | First number ="21" Second number = "0" give message: can't modulus by 0. | Cannot be modulus by 0 | 2024-02-18 | PASS |  | PASS | Tran An Thuyen
5 | MC - 5 | Modulus | Calculate |  | 1. Click on Calculate. | First number ="21" Second number = "5" result = 1 | Wrong result | 2024-02-18 | PASS |  | PASS | Tran An Thuyen

## Clear Function
Module |  | Clear
Code |  | C
Check requirement
Tester |  | Tran An Thuyen
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 1 | 1 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 1 | 1 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | C - 1 | Clear | Clear the value |  | 1. Click on "Clear" button. |  | The value not reset | 2024-02-19 | PASS |  | PASS | Tran An Thuyen